## Sheet1
Activity # | Activity Name | Activity Name Description | # of Days | Start Date | Dependency | Milestone
1 | Planning | Meeting | 2 | 2016-06-13 |  | Information of the project
2 | Planning | Layout Project Plan | 4 | 2016-06-17 | 2;3 | Plan for project features
3 | Analysis | Gather Information | 3 | 2016-06-20 | 3 | Additional Information
4 | Analysis | Create Event Table | 11 | 2016-06-26 | 7 | Finalized Event Table
5 | Analysis | Create Use Case Full Description | 16 | 2016-07-15 | 7;8 | Finalized Use Case Full Description
6 | Analysis | UML Diagrams | 16 | 2016-08-04 | 7;8;9 | Finalized all UML Diagrams
7 | Analysis | Update Wiki | 2 | 2016-08-26 | 7;8;9;10 | Updated Wiki and OneNote
8 | Analysis | Develop GUI | 14 | 2016-08-26 | 3;7;8;9;10 | GUI of the proposed system
9 | Analysis | Project Requirements | 6 | 2016-10-07 | 3;7 | Prepared all project requirements
10 | Analysis | Activity List | 76 | 2016-06-27 |  | Activity List
11 | Analysis | Bluemix | 1 | 2016-09-23 |  | Application for cloud hosting
12 | Analysis | Create WBS | 3 | 2016-10-20 | 14 | WBS
13 | Analysis | Create Gantt Chart | 1 | 2016-10-23 | 14 | Gantt Chart
14 | Design | Design System | 40 | 2016-09-13 | 3;5;7;8;9;10;12;18 | Working system
15 | Design | Design Database | 20 | 2016-09-25 | 3;7;8;9;10 | Database
16 | Design | Update System | 10 | 2016-10-12 | 3;5;7;8;9;10;12;18 | Updated System